## 📊 Dashboard
PROJECT PORTFOLIO TRACKER
Last Updated: April 09, 2026 ¦ Portfolio: AI / GenAI Initiatives
PROJECT HEALTH SUMMARY
PROJECT | DESCRIPTION / OBJECTIVE | STATUS | KEY RISKS | NEXT STEPS | OWNER / DUE DATE
Project 1 – [Name] | Brief one-line description of the project objective and target outcome. | 🟢 On Track | • Risk item 1 • Risk item 2 | • Next step 1 • Next step 2 | Owner Name Due: MM/DD/YYYY
Project 2 – [Name] | Brief one-line description of the project objective and target outcome. | 🟡 Caution | • Risk item 1 • Risk item 2 | • Next step 1 • Next step 2 | Owner Name Due: MM/DD/YYYY
Project 3 – [Name] | Brief one-line description of the project objective and target outcome. | 🔴 At Risk | • Risk item 1 • Risk item 2 | • Next step 1 • Next step 2 | Owner Name Due: MM/DD/YYYY
STATUS LEGEND
🟢 On Track | 🟡 Caution | 🔴 At Risk

## 📅 Gantt Chart
PROJECT TIMELINE — GANTT CHART
[5 empty] | Wk 1 04/06 | [6 empty] | Wk 2 04/13 | [6 empty] | Wk 3 04/20 | [6 empty] | Wk 4 04/27 | [6 empty] | Wk 5 05/04 | [6 empty] | Wk 6 05/11 | [6 empty] | Wk 7 05/18 | [6 empty] | Wk 8 05/25 | [6 empty] | Wk 9 06/01 | [6 empty] | Wk 10 06/08 | [6 empty] | Wk 11 06/15 | [6 empty] | Wk 12 06/22
PROJECT | PHASE | ACTIVITY | OWNER | DUE DATE | 06 | 07 | 08 | 09 | 10 | 1 | 1 | 13 | 14 | 15 | 16 | 17 | 1 | 1 | 20 | 21 | 22 | 23 | 24 | 2 | 2 | 27 | 28 | 29 | 30 | 01 | 0 | 0 | 04 | 05 | 06 | 07 | 08 | 0 | 1 | 11 | 12 | 13 | 14 | 15 | 1 | 1 | 18 | 19 | 20 | 21 | 22 | 2 | 2 | 25 | 26 | 27 | 28 | 29 | 3 | 3 | 01 | 02 | 03 | 04 | 05 | 0 | 0 | 08 | 09 | 10 | 11 | 12 | 1 | 1 | 15 | 16 | 17 | 18 | 19 | 2 | 2 | 22 | 23 | 24 | 25 | 26 | 2 | 2
PROJECT 1 — [Project Name]
| Discovery | Stakeholder Alignment | Lead | 2026-04-10
| Discovery | Requirements Gathering | BA | 2026-04-15
| Design | Architecture Design | Arch | 2026-04-19
| Design | Data Modeling | DS | 2026-04-20
| Build | Pipeline Development | DS | 2026-04-29
| Build | Prompt Engineering | DS | 2026-05-01
| Testing | QA & Validation | QA | 2026-05-08
| Deploy | Pilot Rollout | Lead | 2026-05-13
PROJECT 2 — [Project Name]
| Planning | Use Case Scoping | Lead | 2026-04-11
| Planning | Data Inventory | Analyst | 2026-04-15
| Development | Model Development | DS | 2026-04-26
| Development | Embedding Pipeline | DS | 2026-04-25
| Governance | SR 11-7 Documentation | MRM | 2026-05-02
| Testing | Model Validation | MRM | 2026-05-08
| Deploy | Production Deployment | Eng | 2026-05-14
PROJECT 3 — [Project Name]
| Initiation | Project Charter | PM | 2026-04-08
| Initiation | Resource Planning | PM | 2026-04-11
| Analysis | Current State Analysis | Analyst | 2026-04-18
| Analysis | Gap Assessment | DS | 2026-04-21
| Build | Solution Development | DS | 2026-05-02
| Build | Integration Testing | Eng | 2026-05-04
| Governance | Compliance Review | Risk | 2026-05-08
| Deploy | Go-Live | Lead | 2026-05-13
▲ Today: April 09, 2026 ¦ Yellow column = today ¦ Gray = weekend

## ✅ Task Tracker
ACTIVITY TRACKER — ALL PROJECTS
Track individual tasks and milestones across all projects ¦ Update % Complete and Status as work progresses
PROJECT | PHASE | ACTIVITY / TASK | OWNER | START DATE | DUE DATE | % COMPLETE | STATUS | NOTES / BLOCKERS
▶ Project 1 – [Name]
| Discovery | Stakeholder Alignment | Lead | 2026-04-06 | 2026-04-10 | 100% | Complete | Sign-off received
| Discovery | Requirements Gathering | BA | 2026-04-09 | 2026-04-15 | 80% | In Progress | Final review pending
| Design | Architecture Design | Arch | 2026-04-14 | 2026-04-19 | 50% | In Progress
| Design | Data Modeling | DS | 2026-04-16 | 2026-04-20 | 0% | Not Started | Blocked on arch sign-off
| Build | Pipeline Development | DS | 2026-04-20 | 2026-04-29 | 0% | Not Started
| Build | Prompt Engineering | DS | 2026-04-24 | 2026-05-01 | 0% | Not Started
| Testing | QA & Validation | QA | 2026-05-02 | 2026-05-08 | 0% | Not Started
| Deploy | Pilot Rollout | Lead | 2026-05-09 | 2026-05-13 | 0% | Not Started
▶ Project 2 – [Name]
| Planning | Use Case Scoping | Lead | 2026-04-08 | 2026-04-11 | 100% | Complete
| Planning | Data Inventory | Analyst | 2026-04-10 | 2026-04-15 | 60% | In Progress | Missing 2 data sources
| Development | Model Development | DS | 2026-04-15 | 2026-04-26 | 30% | In Progress
| Development | Embedding Pipeline | DS | 2026-04-18 | 2026-04-25 | 20% | In Progress | CPU-only constraint
| Governance | SR 11-7 Documentation | MRM | 2026-04-26 | 2026-05-02 | 0% | Not Started | Dep: model complete
| Testing | Model Validation | MRM | 2026-05-01 | 2026-05-08 | 0% | Not Started
| Deploy | Production Deployment | Eng | 2026-05-11 | 2026-05-14 | 0% | Not Started
▶ Project 3 – [Name]
| Initiation | Project Charter | PM | 2026-04-06 | 2026-04-08 | 100% | Complete
| Initiation | Resource Planning | PM | 2026-04-08 | 2026-04-11 | 100% | Complete
| Analysis | Current State Analysis | Analyst | 2026-04-11 | 2026-04-18 | 40% | In Progress
| Analysis | Gap Assessment | DS | 2026-04-16 | 2026-04-21 | 0% | Not Started
| Build | Solution Development | DS | 2026-04-21 | 2026-05-02 | 0% | Not Started | Resource risk - TBD
| Build | Integration Testing | Eng | 2026-04-28 | 2026-05-04 | 0% | Not Started
| Governance | Compliance Review | Risk | 2026-05-04 | 2026-05-08 | 0% | Not Started
| Deploy | Go-Live | Lead | 2026-05-11 | 2026-05-13 | 0% | Not Started
SUMMARY COUNTS (auto-calculated)
Total Tasks |  | Complete |  | In Progress |  | Blocked |  | Not Started
23 |  | 4 |  | 6 |  | 0 |  | 13

## ℹ️ How To Use
HOW TO USE THIS TRACKER
SHEET | PURPOSE
📊 Dashboard | High-level portfolio view. Update Project Name, Description, Status, Risks, Next Steps, and Owner for each project.
📅 Gantt Chart | Visual timeline. Replace task activities, owners, and adjust start/duration offsets in the build script, or update the cell values directly.
✅ Task Tracker | Granular task log. Update % Complete (0–100%) and Status dropdown for each row as work progresses.
HOW TO CUSTOMIZE
Rename Projects | Find all cells containing '[Name]' and replace with your actual project names.
Add Tasks | In Task Tracker, copy an existing task row and paste below its project group. Update all fields.
Update Gantt | In Gantt Chart, the colored bars are set to fixed start + duration. Adjust bar fills manually or re-run the build script.
Change Status | In Dashboard, update the STATUS cell text: '🟢 On Track', '🟡 Caution', or '🔴 At Risk'.
Add a 4th Project | In each sheet, duplicate a project block and re-color using a new accent color.
COLOR LEGEND
🔵 Blue bars | Project 1 tasks on the Gantt chart
🟢 Green bars | Project 2 tasks on the Gantt chart
🟣 Purple bars | Project 3 tasks on the Gantt chart
🟡 Gold column | Today's date on the Gantt chart
⬜ Gray columns | Weekend days on the Gantt chart (non-working)